## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Tester A | 2025-09-30 | Log transformation fails when Loan Amount or Income is in negative | Sprint 1 | ML | Logical | Added default value of 0.0 for optional income fields. | 2025-10-01 | Closed
2 | Tester B | 2025-10-05 | Random Forest model overfitting; training accuracy 99% but validation accuracy only 72%. | Sprint 2 | ML | Logical | Performed Hyperparameter tuning using GridSearchCV. | 2025-10-05 | Closed
3 | Data Lead | 2025-10-08 | Chatbot stuck when invalid numeric input is given while login | Sprint 3 | Frontend | User Interface | Added exception handling and validation | 2025-10-08 | Closed
4 | Tester A | 22-10-1025 | Chatbot returns generic 'I don't understand' for valid queries about interest rates. | Sprint 3 | Backend | Maintainability | Retrained/Fine-tuned NLP intent classifier with more financial data samples. | 2025-10-29 | Closed
5 | Tester B | 2025-11-10 | Application times out on Streamlit Cloud due to high memory usage during model loading. | Sprint 4 | DevOps | Standards | Optimized model.pkl size and implemented caching (@st.cache_resource). | 2025-11-15 | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others